## IYCF
Infant and Young Child Feeding Program. Aims to improve the practice of exclusive breastfeeding and complementary feeding by building and sustaining an enabling environment in various settings. The achievement of its outcomes will also require action from the other programs, particularly the Nutrition Promotion for Behavior Change Program, and the Nutrition in Emergencies Programs.
Target Results: |  | Results (2019) |  | 2021 Results
33 percent of infants 5 mos old are exclusively breastfed |  | NNS 2019: 35.1%
22.5% of children 6-23 months old meeting minimum acceptable diet |  | NNS 2019: 9%
Project/Strategy/Output |  | 2017-2018 accomplishments | 2022 target | 2019-2022 accomplishments | Agency/ies involved
Health systems support (DOH, PhilHealth, DILG, LGUs, CSOs)
1. No. of hospitals accredited as mother-baby friendly (% of total)
| a. Government hospitals | 22 (1.11%) Accomplishment should include reports on the number of hospitals with Certificates of Commitment awarded by DOH CHDs. This only counts Certificate of Accreditation. | 2047 |  | DOH
| b. Level II and Level III private hospitals that are training institutions for obstetrics and pediatrics | 32 (1.57%) Accomplishment should include reports on the number of hospitals with Certificates of Commitment awarded by DOH CHDs. This only counts Certificate of Accreditation. | 1919 (for 2020) |  | DOH
| c. Birthing Homes | none | 1699 (for 2020) |  | DOH
2. | No. of hospitals with trained personnel on the care of small baby. | 171 (12%) CSB training and accreditation halted due to COVID-19 restrictions. | 1165 |  | DOH
Community-based health and nutrition support (DOH, LGUs, CSOs)
3. | Maternal, Newborn, Infant and Young Child Nutrition (MNIYCN) of Nutrition in Emergency Plans incorpoated in LGU disaster risk reduction management plans | The guide for DRRM-H is not yet finalized. Hence, integration of NiE II for DRMM-H plan is not yet done. But NNC provided inputs the development of drafting guide for DRRM-H. | / |  | NNC ROs
4. | No. of nutrition counselors trained complementary feeding, relief feeding, etc | Although MNIYCN Harmonized Training Package has rolled out since Q4 of 2019, this is still for retrieval. Requesting to allow DOH to update on W2, October 2020. | 1280 (80%) |  | NNC ROs
5. | No. of human milk banks (HMB) set up and functional | 18 (90%) | 20 (One per region excluding NCR, 2 in Palawan, 1 in Romblon, 1 for Tawi-Tawi and Basilan) |  | DOH
6. | No. of municipalities in the PPAN focus provinces with established pool of trained mother-support groups and trained peer counsellors for lactation management counselling, kangaroo mother care, growth monitoring and promotion, complementary feeding, early child development and acute malnutrition for every barangay. | DOH has not began tracking this. This is integrated into the new harmonized IYCF training package to be rolled out on Q3 2019--and should signal the beginning of tracking. | 722 |  | DOH
7. | No. of barangays with functional community-based support groups on IYCF. | For retrieval. Requesting to allow DOH to update on W2, October 2020. | 33, 623 |  | DOH
Maternity Protection and Improving Capacities of Workplaces on Breastfeeding (DOLE, DOH, Labor Groups, Trade Unions, Employees Confederation; other CSOs
8. | Number of regional tripartite industrial peace councils adopting a resolution advocating or in support of breastfeeding and lactation policy. The Philippine Senate has ratified the International Labor Organization Convention 183 | 8 (47%) Regional Triapartite Industrial Peace Councils (CAR, 2, 7, 8, 10, 11,12) adopting a breastfeeding and lactation support policy; While CHDs have established partnerships for IYCF education in workplaces with labor groups, no formal resolutions have been established in the 9 other regions. | 17 |  | DOLE, DOH, Labor Groups, Trade Unions, Employees Confederation; other CSOs
9. | Government line agencies implementing the CSC –DOLE issuance on RA 10028. | For retrieval from CSC. | 100% |  | CSC
Enforcement of the Milk Code (DOH, DILG, CWC, CSOs, FDA, DOJ, DSWD, DTI)
10. | PPAN focus provinces, cities, and municipalities shall have established integrated monitoring and reporting mechanisms of EO 51, RA 10028 and other related issuances on IYCF in every barangay council for the protection of children (%) | Verification not done for PPAN-focus province. | 32 |  | DOH
11. | Regional Interagency Task Force on EO 51, RA 10028 and other related issuances on IYCF organized | 16 (94%) BARMM unverified. | 17 |  | DOH

## PIMAM
Philippine Integrated Management of Acute Malnutrition Program. Aims to locate the acutely malnourished especially those with severe acute malnutrition, and to provide the needed medical and nutritional intervention.
Target Results (2019): |  | Updated Target Results |  | 2021 Results
At least 90% of identified severe acute malnutrition (SAM) cases in the program areas are enrolled or admitted into the program |  | At least 50% of case load for SAM and MAM identified and are enrolled in ITC or OTC facilities.
At least 75% of severe acute malnutrition cases admitted are discharged as cured |  | At least 75% of identified severe acute malnutrition cases admitted are cured
At least 90% of the near-SAM cases are admitted into the program |  | At least 75% of identified moderate acute malnutrition (MAM) cases are cured.
At least 75% of near-SAM admitted are discharged as cured
Project/Strategy/Output |  | 2017-2018 accomplishments | 2022 target | 2019-2022 accomplishments | Agency/ies involved
Policy development and implementation
12. | PhilHealth package for SAM cases developed and implemented (DOH) | Final package was submitted to PhilHealth last December 2019. The package is currently undergoing internal reviews as part of the approval process. | Package piloted in selected provinces |  | DOH
Service delivery for management of acute malnutrition
13. | Number of PPAN priority provinces/cities with hospitals and field health facilities able to provide Inpatient Therapeutic Care (ITC) (DOH) | 24 (30%) Accomplishments are for 2017 and 2018 only. 2019 reports still to be submitted by LGUs. | 98 (100%) |  | DOH
14. | Number of cities and municipalities in PPAN priority provinces with hospitals and field health facilities able to provide Outpatient Therapeutic Care (OTC) for SAM(DOH) | 191 (54%) (27%) | 779 (100%) |  | DOH
15. | Number of PPAN priority provinces/cities with *functional health service providers network or two-way referral system (DOH) | 24 (30%) Accomplishments are for 2017 and 2018 only. 2019 reports still to be submitted from LGUs. | 98 (100%) |  | DOH
16. | Number of PPAN priority cities and municipalities with health facilities able to provide Outpatient Therapeutic Care (OTC) for MAM (DOH) |  | 779 (100%) |  | DOH
17. | Number of PPAN priority provinces/cities with hospitals and LGU health facilities availing of the developed PhilHealth package for SAM cases (DOH) | Discussions are ongoing on the revision of the final draft package submitted to PhilHealth for board approval Pilot testing to be conducted in 2 AIS (Samar + 1 province TBC) after approval of the package in 2020. | 2 |  | DOH
Capacity building of local implementors
18. | Number of PPAN priority provinces/cities with hospital and field health and nutrition staff trained on the appropriate competencies to identify, treat and manage acute malnutrition and deliver quality services both under routine health program and during emergencies (DOH) | 48 (59%) DOH and some LGUs funded training of trainers and roll-out trainings and several partners such as UNICEF, KMI, WFP, ICM, Save the Children, HOM, and Samaritan's Purse provided technical assistance in the roll out trainings at the local level | 98 (100%) |  | DOH
19. | No. of LGUs with service delivery network established |  | 100 (2020) |  | DOH
20. | No. of LGUs availing of the developed PhilHealth package for SAM cases |  | 100 (2020) |  | DOH
21. | Scheme for bulk procurement of RUTF and RUSF developed and implemented |  | / |  | DOH

## NDSP
National Dietary Supplementation Program. Aims to supplement the inadequate diets of nutritionally vulnerable groups, particularly pregnant women and children 6-23 months old in food-insecure households, and wasted school children. It also aims to supplement the diets of children enrolled in day care centers. Program services will be complemented by those from the other programs, particularly, Nutrition Promotion for Behavior Change, Micronutrient Supplementation, Mandatory Food Fortification, and the Nutrition-Sensitive Program.
Results |  |  | Results (2021)
Pregnant women and lactating mothers enrolled in the program achieve/maintain normal nutritional status
Infants and young children 6-23 months old enrolled in the program achieve/maintain normal nutritional status
Children in child development centers demonstrate normal nutritional status
Children in school demonstrate normal nutritional status
Project/Strategy/Output |  | 2017-2019 accomplishments | 2022 target | 2019-2022 accomplishments | Agency/ies involved
Dietary supplementation of pregnant and lactating women (FNRI, schools and universities offering courses on food science, DOH, NNC, LGUs, CSOs)
22. | Number of food packages/ products) for dietary supplementation of undernourished pregnant women and lactating mothers developed and tested | 1. Menu guide calendar for pregnant and lactating women (2017) 2. Multi-nutrient Extruded Rice Kernels (MNERK) - ordinary rice blended with a multi-nutrient premix: iron, zinc, vitamin A, vitamin B9 and vitamin B12 (extrusion technology, replacing iron with multi-nutrient kernels in rice) 3. Enhanced Nutri-bun - Launched in 29 July 2020. Bread similar to the 1970 nutribun but with improved texture and with added micronutrients iron and vitamin added (52-55 grams per piece; 3 pieces constitute one serving One serving will provide an estimated: 523 kcalories | 2 |  | FNRI, schools and universities offering courses on food science, DOH, NNC, LGUs, CSOs
|  | Products developed but are still for nutritional and sensory evaluation. These products were: Mushroom burger, high-zinc toasted cookies, high-zinc baked cookies, vitamin A orange sweet potato roll with buffalo milk, fish ball | 2 |  | FNRI, schools and universities offering courses on food science, DOH, NNC, LGUs, CSOs
23. | Number of nutritionally-at-risk pregnant women in PPAN focus provinces enrolled/covered in the dietary supplementation program | >The accomplishment of 45,955 is based on the estimated number of pregnant women to be covered by funding support provided by NNC to 5 provinces namely Iloilo, Negros Occidental, Rizal, Pangasinan, Davao Occidental (ECCD F1K Program areas). Of these 5 provinces, only Negros Occidental (covering about 5,735 pregnant women) is a PPAN focus province. Also, reports on accomplishments from LGUs have been incomplete. >13,100 nutritionally-at risk pregnant women in PPAN areas (HAPAG-ASA ) >DM 2020-0327 Interim Guidelines on the Delivery of Nutrition Services in the Context of COVID 19 Pandemic >Should be included in the PPAN accomplishment report being submitted by the LGUs and ROs) to include LGU accomplishments | 227,990 (90%) |  | FNRI, schools and universities offering courses on food science, DOH, NNC, LGUs, CSOs
24. | Number of health and nutrition workers in PPAN focus provinces capacitated on the management of dietary supplementation of pregnant women | >No formal trainings were held but orientations were conducted. However, data on number of workers covered are not available. >Should be included in the PPAN accomplishment report being submitted by the LGUs and ROs to include LGU accomplishments | 43,594 (100% of LGUs covered) |  | FNRI, schools and universities offering courses on food science, DOH, NNC, LGUs, CSOs
25. | Models for delivering dietary supplementation developed and tested | >Kabisig ng Kalahi Batang 1000 protocol >Ateneo Center for Education Development ACED Blueplate Centralized Kitchen (ABCK) model for large-scale school feeding. >Gawad Kalinga Scheme of community kitchens for dietary supplementation of children in public elementary schools >Enhanced Partnership Against Hunger and Poverty (EPAHP) Convergence Program Food items for the feeding programs should be procured locally, preferably from Agrarian Reform Beneficiaries Organizations or ARBOs, or from catering services of beneficiaries of the Sustainable Livelihood Program of the Department of Social Welfare and Development or from recipients of similar livelihood activities of the implementing LGU or NGO. | 1 |  | FNRI, schools and universities offering courses on food science, DOH, NNC, LGUs, CSOs
|  | >Bangsamoro Umpungan sa Nutrisyon (BangUN) 180 days supplementary feeding program by DSWD in Basilan, Sulu, Tawi-Tawi, Lanao del Sur, and Maguindanao for pregnant women, 0-2 yrs old children in the communities, 2-12 yrs old malnourished children in Madaris, DepEd elementary schools not covered in SBFP and children in evacuation sites >Nutrition Intervention Mix program model of FNRI for the internally displaced persons (IDPs) in Barangay Sagonsongan Area 1 in Marawi City for 120 days using using FNRI-developed nutritious Halal products: multi-nutrient extruded rice kernel (MNERK) and BIMON (snack food made of rice-mongo fortified with iron and zinc). This is the first family approach intervention model with four components: gardening, nutrition education, supplementary feeding and income generating project (GarNESupp Plus IGP). BIMON is a snack food made of rice-mongo fortified with iron and zinc. >DOST-PINOY (Package for the Improvement of Nutrition of Infants and Young Children) 2 main strategies: a) Food-based intervention: 120 feeding days of complementary foods among 6-23 months old children and b) Nutrition Education | 1 |  | FNRI, schools and universities offering courses on food science, DOH, NNC, LGUs, CSOs
Dietary supplementation of infants and young children 6-23 months old (DOH, NNC, LGUs, CSOs)
26. | No. of infants and young children 6-23 months old in PPAN focus provinces enrolled in the dietary supplementation program regardless of nutritional status | There is no national funding for dietary supplementation of children 6-23 months old. However, some LGUs (e.g. Camarines Sur, areas in MIMAROPA, NCR) and NGOs like Kabisig ng Kalahi and Hapag-asa are conducting feeding for this age group. >13,627 infants and young children nationwide benefitted from the complementary feeding funded by the LGUs (FNRI report in KRA1) >15, 000 identified undernourished 6-23month old in PPAN areas (HAPAG-ASA ) >Should be included in the PPAN accomplishment report being submitted by the LGUs and ROs to include LGU accomplishments | 1,423,035 (90% of estimated population 6-23 mos old) |  | DOH, NNC, LGUs, CSOs
27. | No. of health and nutrition workers capacitated on the management of dietary supplementation of infants and young children 6-23 months old, including linkages with services of other programs, e.g. promotion of infant and young child feeding, micronutrient supplementation, etc, | >Formal trainings were not conducted by NGAs but Camarines Sur and MIMAROPA LGUs conducted trainings on DSP for infants and young children 6-23 months old. >Should be included in the PPAN report being submitted by the LGUs and ROs) | 100% |  | DOH, NNC, LGUs, CSOs
Dietary supplementation of children in child development centers and supervised neighborhood play (DSWD, LGUs, CSOs)
28. | Children in child development centers (CDC) and supervised neighborhood play (SNP) provided with dietary supplementation (DSWD) | >MC 012, s.2020 Guidelines in the Implementation of the Supplementary Feeding Program During the Community Quarantine Period or Other Similar Emergencies dated 29 April 2020 >As of January 2020 (Cycle 9)- 1,382,205 children in CDCs and 12,197 children in SNP (LGUs served – 1,436 LGUs, 52,949 CDCs) >As of January 2021 (10th Cycle), 835, 845 children served in CDCs and 146 children served in SNPs | 80% Budget 2021: Php 3,830,416,000 2022: still for proposal |  | DSWD, LGUs, CSOs
29. | Day care workers capacitated on the management of food supplementation, including the identification of under or overnutrition, and linkages with services of other programs e.g., nutrition education, in percent | >Orientation to the Regional NDs/focal persons on the guidelines >Trainings were held at the regional level but data were not consolidated data nor made available at this time. >No budget for trainings at the national level. Program guidelines and updates on its implementation are discussed during the Program Review and Evaluation Workshop (PREW) >No data available for 2020 | 100% |  | DSWD, LGUs, CSOs
Dietary supplementation of wasted school children (DepEd, LGUs, CSOs)
30. | No. of wasted school children (SC) in grades K-6 provided with supplementary feeding (DepED) | Deped Order 39, S. 2017 Operational Guidelines on The Implementation of School-Based Feeding Program For School Years 2017-2022 Targets: 2017 -1,823,443 2018- 1,791,931 2019- 1,836,793 | 100% |  | DepEd
31. | No. of teachers implementing feeding capacitated on the management of the dietary supplementation including linkages with services of other programs. (DepED) | >Training of Trainors for the promotion of School Feeding Standards for Quality Management of The School-Based Feeding Program (2017) >Conduct of Program Implementation Review (PIR) and Planning Workshop on School Based Feeding Program >National Capacity Building on the Integrated School Nutrition Model (ISNM) - 2018 | 100% |  | DepEd
Support component (FNRI; small- and medium-scale enterprises. LGUs and SUCs adopting FNRI-developed and other related technologies)
32. | No. of Complementary Food Processing Facilities facilities of complementary, supplementary food for children and pregnant women established and operationalized. (FNRI) | 37 existing Complementary Food Processing Facilities (CFPF) established >(17 regions, 33 provinces) >33 currently operational >8 new CFPFs being established | 60 |  | FNRI
33. | No. of LGUs procuring from the existing food plants enrolled in the program and increased volume of transactions with food plants by national government agencies with food plants (FNRI) | >Some LGUs included in the food packs products from several CFPF. >Data on the number of LGUs procuring from the plants to be requested from FNRI | 80% |  | FNRI
Cross-cutting concerns
34. | Guidelines on dietary supplementation for the First 1000 Days (F1K) formulated, approved, disseminated, and implemented | >DM 2020-0327 Interim Guidelines on the Delivery of Nutrition Services in the Context of COVID 19 Pandemic >DM 2020-0261 Interim Guidelines on the Continuous Provision of Maternal Health Services during COVID-19 Pandemic >DM No 2019-0365 Interim Guidelines on the Use of Lipid-Based Nutrient Supplement Small Ouantitv (LNS-SQ) for Pregnant and Lactating Women and Young Children Ages 6-23 months to prevent stunting | Guidelines Implemented |  | DOH
|  | >Deped Order 39, S. 2017 – Operational Guidelines on The Implementation Of School-Based Feeding Program For School Years 2017-2022 >DO 036 s 2019 Guidelines on the Implementation of School-Based Feeding Program-Milk Feeding Program Component >DO 15, S. 2018 – Supplemental Guidelines on the Implementation of School-Based Feeding Program For Fiscal Year 2018 dated 08 Feb 2017 | Guidelines Implemented |  | DepEd
|  | >MC 012, s.2020 Guidelines in the Implementation of the Supplementary Feeding Program During the Community Quarantine Period or Other Similar Emergencies dated 29 April 2020 >MC 03, s.2019 Revised Procedures on the Implementation of the Supplementary Feeding Program Based on the Amended Administrative Order No. 04 series 2016 >AO 07, s.2017 Amendments on AO NO.3 otherwise known as Supplemental Guidelines for the Twice a Day feeding >AO 03, s.2017 Supplemental Guidelines to Administrative Order No. 04 Series of 2016 Otherwise Known as Amended Guidelines in the Implementation of the Supplementary Feeding Program (SFP) | Guidelines Implemented |  | DSWD
|  | >Dietary Supplementation for the First 1000 Days >Guidelines on the Early Childhood Care and Development in the First 1000 Days (ECCD F1K) Program in the Context of COVID 19 Pandemic | Guidelines Implemented |  | NNC
35. | Guidelines for the acceptance of donations for dietary supplementation programs per RA 11037 formulated, approved, disseminated, and implemented (NNC) | As stated in RA 11037 “Section 11. Tax Exemption. Any donation or request made to the NGAs or any of the aforementioned government agencies including LGUs for the Program shall be exempt from donor’s tax: Provided, that donations in kind shall be approved by the NGAs concerned upon the recommendation of the NNC in the case of food products and the DOH, in the case of vaccine and supplements, as the case may be respectively” | Guidelines Implemented |  | NNC
36. | Five-year plan for the implementation of National Feeding Program per RA 11037 formulated and disseminated (DSWD and DepED) | As stated in RA 11037 | Guidelines Implemented |  | DSWD and DepEd
37. | IRR of RA 11037 formulated and disseminated (DSWD and DepED) | “Masustansyang Pagkain para sa Batang Pilipino Act”approved in 20 June 2019 Ceremonial Signing: 7 October 2019 | IRR Implemented |  | DSWD and DepEd
38. | RA 11148 – Kalusugan at Nutrisyon ng Mag-Nanay Act (2018) approved and disseminated | On 29 November 2018, the President signed Republic Act 11148 or the “Kalusugan at Nutrisyon ng Mag-Nanay Act.” The law is focused on strengthening health and nutrition program for pregnant women and infants. With the enactment of this law, health and nutrition services will be provided to all Filipinos who are “nutritionally at risk.” | RA 11148 implemented
39. | RA 11148 IRR formulated, approved, disseminated, and implemented | >Ceremonial signing on 2 May 2019 >RA 11148 IRR Dissemination Forum (23 July, 27 July, 30 July, August 4) >Comprehensive Sustainable Strategy and Manual of Operations being formulated | IRR Implemented
40. | JMC on the implementation of NDSP under PPAN | Target: within August | Guidelines implemented
41. | Number of ARBOS/SLPAs/NIAs/local cooperatives with marketing agreement with DSWD, DepEd and NNC | Lumad sa Adgawan Multi-Purpose Cooperative (LAMUPCO) successfully joined and won the bidding with a total contract of PhP 16,000,000.00 for CY 2019. A total of 750 Agrarian Reform Beneficiaries benefitted from this partnership. Moreover, 55 Child Development Centers and 1,680 CDC children were served. For CY 2020 implementation of SFP, the same ARBO won the bidding and they will supply the food requirements amounting to PhP 15,000,000.00. | / | No. of ARBOs/SLPAs/NIAs/ local cooperativrs engaged SFP: 1,623 (2019) 47 (2020) 1,566 (2021) | DSWD

## Promotion
National Nutrition Promotion Program for Behavior Change. Aims to facilitate the adoption of positive practices that will impact on nutrition. It highlights the interplay of interpersonal, community communication, mass media and social media. It will engage media organizations, particularly the media moguls, owners, producers, social media bloggers and print news and opinion writers, to actively disseminate key nutrition messages. It supports the other PPAN programs. It will be supported by the appropriate policy cover to create an environment that will facilitate the adoption of desired practices.
Results (As submitted to the NNC Governing Board on 24 April 2019) |  | Actual Results (2019) |  |  | Results (2021)
Improvement in the following behaviors: |  | Behavior |  | Status | Status
Breastfeeding |  | Pregnant women undergoing 4 or more ante-natal visits
Complementary feeding |  | 5 month-old infants who are exclusively breastfed |  | 35.1% ENNS 2019
Handwashing (but the WASH) |  | Infants and young children 6-23 months old meeting minimum adequate diet |  | 9.9% ENNS 2019
Use of iodized salt |  | Practice of Handwashing |  | No measure
Compliance to micronutrient supplementation (increased coverage) |  | Households using adequately-iodized salt |  | 37.2% ENNS 2018
Healthier diet; physical activity |  | Improvement in Physical activity |  | 40.6%
Project/Strategy/Output |  | 2017-2018 accomplishments | 2022 target | 2019-2022 accomplishments | Agency/ies involved
42. | Social and Behavior change communication Plan developed | Consulting firm to assist in formulating the strategy has been engaged. Development of the strategy is ongoing Formative research on infant and young child feeding was done in 2017. Results guided the development of related materials (See item __). DOH formulated its communication plan on infant and young child feeding. A communication plan was developed for the national salt iodization program (NSIP) for 2018 – 2022. | 1 (2021)
43. | Organization of National TWG for Nutrition Promotion Program for Social and Behavior Change |  | /
| a. Terms of Reference for the organization of NTWG finalized and approved by NNC Technical Committee |  | 1 (2020)
| b. Meetings of NTWG members conducted as scheduled |  | 6
| c. Issuance of RNC resolution GB resolution to include regional Health Education and Promotion Officer (HEPO), regional PIA Information Officer as member of the regional nutrition committees subgroup or TWG in-charge of advocacy and communication activities |  | 1 (2021)
44. | Nutrition information resource center set up and functional at the national and regional levels, which shall serve as a permanent repository of nutrition promotion materials and other resources |  | 17
45. | Provinces implementing the national communication strategy (e.g. Idol ko si Nanay, NGF, 10 Kumainments) | 12 (39%) F1K provinces 19 (100%) PPAN focus provinces The F1K Program areas conducted Idol Ko Si Nanay sessions, reaching about ___ mothers and child caregivers or about ___% of the estimated number of children 0-23 months old in the program areas. | 32 Updated PPAN focus provinces
46. | Development of SBCC materials | Notwithstanding the ongoing formulation of the strategy or plan, promotional efforts continued to be pursued, as follows: a. Promotion of Unang Yakap, Hakab Na with Breastfeeding Pinays, Reaching out to IPs, 10 steps to successful breastfeeding, b. Development of TV and radio plug and other materials on iodized salt c. Airing of an existing plug on salt iodization, ___ exposures in _____ d. TV plugs on breastfeeding, Reporting platform for EO 51 and RA 10048 violators with breastfeeding promotion components | /
e. Promotion of nutrition and nutrition-related information thru social media to reach and connect with broader audience including the target population and local health workers f. DOST Pinoy-related accomplishments g. Conduct of Nutrition School on the Air with __ sessions in 2017, ___ in 2018, and ___ in 2019 h. Airing of 48 episodes of Katumbas ay Biyaya over DZRH every year from 2017 to 2019. Each episode includes a brief drama and a discussion on a nutrition-related topic. i. Airing of 48 episodes of Radyo Mo sa Nutrisyon every year from 2017-2019 over DZXL. Each episode tackles a nutrition and related concern or a government program to address malnutrition
j. Airing of __ episodes of a television ___, Doc Ricky, Pedia ng Bayan over ABS-CBN. k. 50 Nutriskwela community radio stations set up in areas that have limited access to major radio networks l. Annual observation of Nutrition Month with themes on ___ in 2017, ___ 2018 and ___ in 2019 m. Use of BIDANI approach in 12 state universities and colleges, covering around 700 barangays. Piloting of Participative Nutrition Enhancement Promotion in two areas n. Integration of health and nutrition sessions in family development sessions for participants in the conditional cash transfer program, and in parents’ effectiveness for participants in child development centers
47. | Integration of nutrition in the sectoral policies, programs, and materials |  | / |  | NNC GB Member Agencies
48. | Development of SBCC guidelines |  | 19 (2021) |  | DOH, NNC
49. | Monitoring and evaluation studies |  | 1 |  | DOH, NNC

## MSP
Micronutrient Supplementation Program. Focuses on the provision of pharmaceutically-prepared vitamins & minerals for treatment and prevention of specific micronutrient deficiency to complement sustainable food-based approaches (e.g. food fortification and diet diversification) to address deficiencies in micronutrients. (DOH, LGUs, CSO, development partners)
Results: |  |  | Results (2018) | Results (2021)
90% of pregnant women receive and take-in iron-folic acid supplementation as per guidelines |  |  | 54.1%
90% of pregnant and lactating women in areas endemic with iodine deficiency disorders receive iodized oil capsules
90% of children 6 mos – 11 months old receive high-dose vitamin A once a year |  |  | 96.39%
90% of children 12 – 59 months old receive high-dose vitamin A twice a year |  |  | 49.7%
90% of children 6-11 months old receive adequate supply of micronutrient powder as per guidelines |  |  | 23.37%
90% of children 12-23 months old receive adequate supply of micronutrient powder as per guidelines |  |  | 39.16%
90% of adolescent females receive and take-in iron-folic acid supplements as per guidelines
Project/Strategy/Output |  | 2017-2018 accomplishments | 2022 target | 2019-2022 accomplishments | Agency/ies involved
Health systems support (DOH, PhilHealth, LGUs, CSOs, private birthing facilities, private health facilities with maternity services)
LOGISTIC and SYSTEM
50. | Logistics systems for micronutrient supplements assessed and improved to ensure micronutrient supplements are available in all health facilities at all times | An assessment of the Nutrition supply chain management of DOH was conducted through the Technical Assistance of UNICEF. The results of the assessment and the recommendations were presented to a workshop of supply officers and to the Women, Men and Children's Health Development Division of DPCB for appropriate action The assessment points to some delays in the procurement, delivery of the supplies and its distribution to the Centers for Health Development and the Local Government Units. This also prompted the DOH to plan to invest in an electronic logistics information system (eLIS) | / |  | DOH
51. | Electronic logistics and information system (e-LIS) operational | Electronic logistics information system (e-LIS) software will be procured in 2021 and expected to be operational by 2022. The system can track the incoming and outgoing commodities in the DOH warehouses and can generate real-time inventory to prevent slow movement of commodities and their expiration while in storage | / |  | DOH
52. | Delivery and utilization of nutrition commodities in various health facilities tracked through the Pharmaceutical Management Information System | Pharmaceutical Management Information System (PMIS) was implemented by DOH in 2019 to track the delivery and utilization of DOH commodities including nutrition commodities provided to LGU health facilities. Data can be generated from the system monthly at the national and regional levels to determine stock outs | / |  | DOH
53. | Scheme for paying for micronutrient supplementation through PhilHealth under the Universal Health Care Law developed and implemented | Guidelines on individual-based and population based interventions drafted where the micronutrient supplements will be included by primary health packages to be financed by Philhealth | / |  | Philhealth
PROCUREMENT, DISTRIBUTION and AVAILABILITY of SUPPLIES
54. | Supplies of iron-folic acid for pregnant women procured | 2017: 53% 1,946,296 2018: 55% 2,052,026 | 3,072,610 (100%) |  | DOH
55. | Supplies of iron-folic acid for pregnant women distributed |  | 3,072,610 (100%) |  | DOH
56. | Supplies of iodized oil capsules for pregnant and lactating women procured |  | 3,072,610 (100%) |  | DOH
57. | Supplies of iodized oil capsules for pregnant and lactating women distributed in areas endemic to iodine deficiency |  | 3,072,610 (100%) |  | DOH
58. | Supplies of vitamin A capsules for children 6 mos-5 years old procured | 2017: 57% 7,266,346 2018: 55% 7,123,461 | 11,022,705 (100%) |  | DOH
59. | Supplies of vitamin A capsules for children 6 mos -5 years old distributed |  | 11,022,705 (100%) |  | DOH
60. | Supplies of micronutrient powder for young children 6-23 months old are procured |  | 3,526,674 (100%) |  | DOH
61. | Supplies of iron-folic acid tablets for adolescent females in poor areas procured | for young children 6-23 months old are distributed | 100% |  | DOH
62. | Supplies of iron-folic acid tablets for adolescent females in poor areas distributed |  | 100% |  | DOH
CAPACITY BUILDING
63. | A regular technical updating established for sustainable system of delivering training for the regional nutrition coordinators and other technical staff at all levels of service delivery as part of the human resource development. A module to track the commodity may be developed. | DOH updated the Manual of Operations on Micronutrient Supplementation, training to be conducted in 2020 | / |  | DOH
ADVOCACY and COMMUNICATION PLAN
64. | Advocacy to LGUs to invest on additional micronutrients to ensure intake of these nutrition supplements by at least 90% of the target eligible population |  | / |  | DOH
65. | Communication plan targeting beneficiaries and parents and caregivers to take the recommended dosage and number of micronutrient supplements |  | / |  | DOH
66. | No. of national communication | UNICEF developed a video, fans, flyers on MNP and iron-folic acid; pretesting completed | / |  | DOH
MONITORING and EVALUATION
67. | Monitoring and Evaluation through the FHSIS and conduct of PIR | / | / |  | DOH
68. | All regional technical teams monitoring activities are fully funded and hold an annual program implementation review (PIR) |  | / |  | DOH

## FF
Mandatory Food Fortification Program. Involves the addition of one or more nutrients to rice, flour, cooking oilas mandated by RA 8976 and to salt as mandated by RA 8172, or as prescribed by the NNC Governing Board.
Objectives | (1) Improve agricultural productivity and income of nutritionally-vulnerable population
(2) Improve physical access to food of nutritionally-vulnerable population
Target Results: |  | Results (2019) |  | 2021 Results
1. 50% of registered wheat flour millers, importers, distributors and traders fortifying and/or ensuring wheat flour is fortified with vitamin A and iron according to standards |  | 50 flour millers are fortifying flour with vitamin A and Iron. Results of the 2019 APMSP showed that out of the 48 samples tested, only 4 samples conformed to the standard level of vitamin A while 19 samples conformed to the standard level of iron.
2. 50% of registered cooking oil refiners, importers, distributors, and traders fortifying and/or ensuring cooking oil is fortified with vitamin A according to standards |  | Results of the 2019 APSMP showed that out of the 36 samples tested, all were non-compliant to fortification standards.
3. 25% of rice requirements of government agencies implementing social safety net programs use iron fortified rice for distribution or food preparation (DepEd SBFP, DepEd SFP, DSWD Disaster preparedness and response |  | Actual volume of iron-fortified rice requirements of the identified SSNPs for the years 2021 onwards will be determined.
4. _____% of sugar for home consumption is fortified with vitamin A according to acceptable standards (still to be determined with subTWG sugar) |  | For discussion with the Sub-TWG on sugar if this indicator will be removed.
5. 70% of imported salts and all local salt should be iodized based on the acceptable standards |  | Partial 2019 APMSP results revealed that only 5 out of 25 salt products conformed to the standard.
6. 90% of households use adequately iodized salt |  | Latest data from the 2018 NNS reported that only 37.2% of households used adequately iodized salt.
Project/Strategy/Output |  | 2017-2019 accomplishments | 2022 target | 2019-2022 accomplishments | Agency/ies involved
Overall Program Coordination, Monitoring and Evaluation
69. | Reorganization of the TWG on Food Fortification and Sub TWGs on flour, oil, sugar, flour and processed foods and salt | TWG’s first meeting held on 13 May 2020 and agreed on the reorganization of the sub-TWGs | /
70. | RA 8976 reviewed and updated |  | 1 (2021) |  | NNC
71. | Strategic Plan for mandatory food fortification formulated and approved by the NNC Governing Board | In preparation for the formulation of the strategic plan on food fortification, a consulting group has been engaged to assess implementation of RA 8976. Report is targeted to be presented/completed by 3rd quarter of 2020 | 1 (2021) |  | NNC
72. | Strategic plan on mandatory fortification of cooking oil, rice, sugar, and wheat flour implemented |  | / |  | FDA, rice, flour, cooking oil, sugar industries, FNRI, DOH, SRA, PCA, NFA, NGAs, NGOs, CSOs, development partners
73. | Review of implementation and formulation of guidelines on voluntary fortification of processed foods | List of products with SPS from 2014-2018 updated by FDA and is noted to include a number of sugar-sweetened beverages, chips and the like. | 1 (2020)
74. | National health promotion and communication plan on mandatory food fortification developed and implemented as part of the Nutrition Promotion Program for Behavior Change | TV plugs on Saktong Iodine sa Asin were aired in 2018, total of __ exposures. A communication plan was developed and implemented for the NSIP in 2018-2019. Advocacy materials to implement the NSIP communications plan were developed and will be finalized in 2020. Advocacy materials for Compostela Valley Province Rice Fortification Program, and Gawad Kalinga feeding were developed, pretested, and finalized. Reproduction and dissemination targeted in 2020. | / |  | DOH
Strengthened compliance monitoring system
75. | Management information system operationalized and feedback system the with industry and TWG strengthened | According to FDA, monitoring of fortified foods has been integrated in the FDA's routine regulatory monitoring system (annual post surveillance). Regional Offices are submitting reports based on collection and APMSP Schedule. No regulatory monitoring for iron fortified rice and sugar. | / |  | DOH, NNC, FDA, NFA, SRA, PCA
76. | Scheme for engagement of CSOs in monitoring developed, tested and implemented | Need to identify lead agency to anchor this project. | Development |  | NNC, FDA, DOH
WHEAT FLOUR
77. | Policy on mandatory folic acid fortification of flour reviewed and approved by the NNC Governing Board | Consultation with flour industry conducted, indicated that the industry is willing to comply once related policies are adopted. Studies on stability, acceptability, and efficacy will first be pursued before adoption of the policy. | 1 |  | NNC
78. | Studies on retention, stability, and acceptability | Proposal of FNRI on the “Development of Wheat Flour Fortified with vitamin A, Iron, and Folic Acid” was not approved for financial support. NNC to assist FNRI in looking for possible source of funding and/or endorse to DOH | 1 |  | FNRI
RICE
79. | Policy on the use of iron fortified rice in social safety net approved by the NNC Governing Board | Signed by: DA, DILG, DBM, DOLE, NEDA, and DTI Still for signature of: DepEd, DOST, DSWD, PhilCAN, and PLCPD | / (2020) |  | NNC
80. | Approved policy on the use of iron-fortified rice in social safety net programs implemented and monitored | Programs should be defined per year from DOH, DSWD, DepEd (2020) and other departments (2021-2022) | 1 |  | DOH, DSWD, DepEd
81. | FDA guidelines on use of extruded iron rice fortificant approved | Awaiting updates for rescheduled public consultation | 1 (2020) |  | FDA
SALT
82. | Amended Revised IRR of RA 8172 approved | Per FDA, Republic Act No. 8172 is subject to review to have a sunset clause. Amended Revised IRR to be submitted to the NNC Governing Board for approval and signature | 1 (2020) |  | NNC
83. | Strategic plan of the NSIP implemented | Key accomplishments were on the following: 1. Technical support on salt iodization to salt manufacturers. 2. Monitoring of salt and salt products in the market through FDA, RBATFs and salt checkpoints in some parts of the country. 3. Development and testing of monitoring tools for use of RBATFs. | / |  | DOH, NNC, FDA, ITDI, Salt manufacturers

## NiE
Nutrition in Emergencies Program. Involves the provision of nutrition services to populations affected by a disaster or emergency particularly in the response and recovery phases. It also involves emergency preparedness to ensure that the capacity to respond well is present.
Target Results: |  | Results (2019) |  | 2021 Results
Nutrition protection in emergencies integrated in overall disaster risk reduction and management efforts in the 50 priority provinces of the NiEm Program |  | Ongoing and continuing
Project/Strategy/Output |  | 2017-2018 accomplishments | 2022 target | 2019-2022 accomplishments | Agency/ies involved
Policy development, updating and dissemination
84. | AO on Nutrition in Emergencies developed and disseminated (DOH, NNC, UNICEF) | Not done, to be done after finalization of the revised NiE policy guide. | 1 (2021) |  | DOH, NNC, UNICEF
85. | 2009 Policy Guide on Nutrition in Emergencies updated and disseminated (NNC) | The assessment of the implementation of the policy guide was done in 2019. The validation and consultation workshop with the Nutrition Cluster members and selected regional participants and the revision of the policy using the results of the assessment and workshop outputs were done in January 2020. The next step is the presentation of the revised NiE policy to the NNC Technical Committee for review and approval. | 1 (2021) |  | NNC
86. | DRRM-H-NiE Plan developed/updated and integrated in the DRRM-H Plan/LNAP at the national, regional, provincial, city/municipal levels (DOH, NNC, LGUs) | The NiE National Strategic Plan 2017-2022 was formulated and approved by the NNC Governing Board through NNC Governing Board Resolution No. 2, Series 2018 (24 January 2018). Next steps are the updating of the NiE Strategic Plan and its integration in the DRRM-H Plan considering the final DRRM-H planning guide issued by the DOH and the AO on the National Policy on DRRM-H. However, strategies to integrate DRRM-H-NiE Plan in the DRRM-H plan was included in the revised NiE training manual used during the regional level Training of Trainers (ToT) in 2019 and will be used in the upcoming virtual and face-to-face trainings for the provincial and municipal/city levels in 2020-2022. |  |  | DOH, NNC, LGUs
a. | - National level | The NiE National Strategic Plan 2017-2022 was formulated and approved by the NNC Governing Board through NNC Governing Board Resolution No. 2, Series 2018 (24 January 2018). Next steps are the updating of the NiE Strategic Plan and its integration in the DRRM-H Plan considering the final DRRM-H planning guide issued by the DOH and the AO on the National Policy on DRRM-H. However, strategies to integrate DRRM-H-NiE Plan in the DRRM-H plan was included in the revised NiE training manual used during the regional level Training of Trainers (ToT) in 2019 and will be used in the upcoming virtual and face-to-face trainings for the provincial and municipal/city levels in 2020-2022. | 1 (100%) (2021)
b. | - Regional level | The NiE National Strategic Plan 2017-2022 was formulated and approved by the NNC Governing Board through NNC Governing Board Resolution No. 2, Series 2018 (24 January 2018). Next steps are the updating of the NiE Strategic Plan and its integration in the DRRM-H Plan considering the final DRRM-H planning guide issued by the DOH and the AO on the National Policy on DRRM-H. However, strategies to integrate DRRM-H-NiE Plan in the DRRM-H plan was included in the revised NiE training manual used during the regional level Training of Trainers (ToT) in 2019 and will be used in the upcoming virtual and face-to-face trainings for the provincial and municipal/city levels in 2020-2022. | 17 (100%) (2021)
c. | - Provincial level | The NiE National Strategic Plan 2017-2022 was formulated and approved by the NNC Governing Board through NNC Governing Board Resolution No. 2, Series 2018 (24 January 2018). Next steps are the updating of the NiE Strategic Plan and its integration in the DRRM-H Plan considering the final DRRM-H planning guide issued by the DOH and the AO on the National Policy on DRRM-H. However, strategies to integrate DRRM-H-NiE Plan in the DRRM-H plan was included in the revised NiE training manual used during the regional level Training of Trainers (ToT) in 2019 and will be used in the upcoming virtual and face-to-face trainings for the provincial and municipal/city levels in 2020-2022. | 34 (42%) (2021)
d. | - Municipal/city level | The NiE National Strategic Plan 2017-2022 was formulated and approved by the NNC Governing Board through NNC Governing Board Resolution No. 2, Series 2018 (24 January 2018). Next steps are the updating of the NiE Strategic Plan and its integration in the DRRM-H Plan considering the final DRRM-H planning guide issued by the DOH and the AO on the National Policy on DRRM-H. However, strategies to integrate DRRM-H-NiE Plan in the DRRM-H plan was included in the revised NiE training manual used during the regional level Training of Trainers (ToT) in 2019 and will be used in the upcoming virtual and face-to-face trainings for the provincial and municipal/city levels in 2020-2022. | 111
87. | NNC Governing Board resolution on information management in emergencies approved and disseminated (NNC) |  | 1 |  | NNC
88. | ECCD-F1K Manual of Operations mainstreamed emergency setting (DOH, NNC, UNICEF) |  | 1 (2020) |  | DOH, NNC, UNICEF
89. | Nutrition Cluster Advisories issued for emergencies and disasters (National Nutrition Cluster) | Two (2) advisories issued specific for COVID-19 pandemic | At least one for major events |  | National Nutrition Cluster
Capability development
90. | NiE training modules and materials reviewed, updated, and disseminated (DOH, NNC, UNICEF, WFP) | The training manual on Nutrition in Emergencies was reviewed and updated in 2018-2020: Trainer’s Manual on NiE, Manual on NiE, LCE Handbook, NiE Reference Handbook, and Job Aids. Capacity Gap Analysis, which identified competencies, was completed and used as basis for updating the training modules. Simulation exercises were embedded in the training. The target in 2021 is to have these manuals reporduced and disseminated to all trained Nutrition Clusters at the national, regional, provincial, and municipal/city levels. | 1 (2021) |  | DOH, NNC, UNICEF, WFP
91. | Regions, provinces, cities and municipalities with staff trained on NiE and Information Management (IM) (DOH, NNC, LGUs, CSOs, development partners) |  |  |  | DOH, NNC, LGUs, CSOs, development partners
a. Nutrition in Emergencies
a.1 | Regional Level | Training of Trainers was also completed in 2019 with a total of 58 staff trained (batch 1: 26; batch 2: 32) from 16 (94%) regions, excluding BARMM. | 1 (2020)
a.2 | Provincial Level |  | 47 (2020)
a.3 | Municipal/City Level |  | 411 (60.5%)
b. Information Management
b.1 | Information Management | Information management (IM) tools were developed and tested. IM tools were reduced from 9 to 6 tools. Three tools were merged into one tool (Report Form A, Report Form B, and Dashboard). Functionality checklist was removed since its components will be added in the functionality checklist used by local nutrition committees to avoid duplication and additional forms at the local level. For 2020-2022, virtual and face-to-face training on NiE and IM (combined) will be conducted at minimum of 1 batch per region. There will be a mixture of participants from provincial and municipal/city levels depending on the results of the Training Needs Assessment. |  |  | NNC
b.1 | Regional Level | 17 (100%) regions attended the IM training in 2019. A total of 30 staff were trained. Participants were composed of Nutrition Officers of Regional NNC offices, and DOH Nutritionist-Dietitians and/or DRMM-H managers of Regional DOH-CHDs. Regional IM trainers will conduct provincial training roll out. | 17 (2019) |  | NNC
b.2 | Provincial Level | 68 (84%) | 13 (2020) |  | NNC
b.3 | Municipal/City Level |  | 411 (60.5%) |  | NNC
Prepositioning and resource mobilization
92. | Key supplies prepositioned and mobilized within 24-48 hours, as needed/requested (DOH, LGUs, development partners) | DOH prepositioned supplies of vitamin A capsules, iron-folic tablets, micronutrient powder, RUTF, RUSF, breastfeeding kits, and other nutrition supplies. NNC and DOH procured MUAC tapes for children and adults. DSWD has its established and functional warehouses at the regional level, which can be tapped for the temporary storage of nutrition supplies. | / |  | DOH, LGUs, development partners
Promotion and communication
93. | Communication package for NiE developed and disseminated (DOH, NNC, development partners) | Communication plan developed in 2017-2019 and reviewed and updated in 2020. Communication materials developed and disseminated from 2017-2019 thru print at the sub-national level. Dissemination of materials thru different online platforms (social media and YouTube) started in 2020. | 1 (2020) |  | DOH, NNC, development partners
Inter- and intra-cluster coordination
94. | Nutrition Clusters at the national, regional, provincial, city/municipal levels organized (DOH, NNC, LGUs, NGOs, development partners) |  |  |  | DOH, NNC, LGUs, NGOs, development partners
a. | National Level | 1 (100%) | 1 (100%)
b. | Regional Level | 17 (100%) | 17 (100%)
c. | Provincial Level |  | 0 (0.0%)
d. | Municipal/City Level |  | 411 (60.5%)
95. | National, regional and local nutrition clusters respond to emerging situations and use IM tools for reporting (DOH, NNC, national, regional and local nutrition clusters) | Members of National and Regional Nutrition Clusters were mobilized and utilized IM tools during Mindanao Earthquake, Polio, Measles, Taal eruption, and COVID-19 Pandemic. | / |  | DOH, NNC, national, regional and local nutrition clusters
96. | All other elements of the NiE National Strategic Plan implemented (National Nutrition Cluster) | Conversations on a nutrition-oriented family food pack continued. On 31 March 2020, the Nutrition Cluster's modified enhanced family food pack, i.e. 1) FFP for Luzon/Visayas, 2) FFP for Mindanao, and 3) FP (complementary food) for older infants and young children (6-23 months), was endorsed to the DSWD. The DOH released DM No. 2020-0231 on Standardized Regulation of Donations Related to EO 51 and DM No. 2020-0237 on Interim Guidelines on the Delivery of Nutrition Services in the Context of COVID-19 Pandemic. Other issuances, advocacy and communication materials were developed and disseminated to ensure nutrition management during the COVID-19 pandemic. | / |  | National Nutrition Cluster
Information management
97. | Operational guidelines on nutrition assessment, monitoring and evaluation developed and disseminated (NNC) | NNC has drafted the guidelines on the operationalization of Information Management tools. Next target is to update the guidelines to include nutrition assessment in normal times and in the new normal (prevention and mitigation phase). | / (2020) |  | NNC
98. | Capacity maps for national, regional, provincial, and city/municipality levels generated 1st quarter of every year (National, regional and local nutrition clusters) |  | 1 (2021) |  | National, regional and local nutrition clusters
a. | National Level | Capacity mapping tool was revised and updated based on the needs of national and regional nutrition clusters; initial capacity map was developed in 2018 using NiE training reports; ongoing updating of the 2019-2020 capacity map to also include inputs from the National Nutrition Cluster members. Capacity map is to be accomplished 1st quarter of every year. | 1 (100%)
b. | Regional Level |  | 17 (100%)
c. | Provincial Level |  | 81 (100%)
d. | Municipal/City Level |  | 419 (62%)
99. | Monitoring and evaluation framework for Nutrition Cluster Strategic Plan updated (National Nutrition Cluster) |  | 1 (2021) |  | National Nutrition Cluster

## OOMP
Overweight and Obesity Management and Prevention Program. Involves the promotion of healthy eating environments and healthy lifestyle; also involves the management of those already overweight and obese
Target Results: |  | Results (2019) | Updated Target Result |  | 2021 Results
At least 50% of children in day care centers, school children, adolescents, and adults are covered by healthy eating environment |  | Organized Philippine Overweight and Obesity Management Task Force and Strategic Plan | No further increase in the prevalence of overweight and obesity among preschool and school children, adolescents and adults
At least 50% of children in day care centers, school children, adolescents, and adults are covered by the promotion of healthy lifestyle |  | Policies passed and issued and advocacy plans promoting healthy eating environments through regulation of production, manufacture, marketing, selling and consumption of unhealthy food and beverages and advocacy plans
Policies passed and issued and advocacy plan promoting active lifestyle
Policies/guidelines on management of overweight and obesity
Project/Strategy/Output |  | 2017-2018 accomplishments | 2022 target | 2019-2022 accomplishments | Agency/ies involved
100. | Organization of the OOMP Task Force |  | 1 (2020) |  | NNC
101. | Conduct of Landscape Analysis on Childhood Overweight and Obesity |  | 1 (2021) |  | UNICEF, NCP
102. | Updated guidelines on physical activity for Filipinos |  | 1 (2021) |  | DOH-DPCB
103. | Conduct of policy forum conducted on healthy eating environment |  | / |  | DOH-DPCB

## Nutrition Sensitive
Nutrition-Sensitive Program. Involves tweaking the design of ongoing development programs to contribute to achieving nutritional outcomes Results:
Target Results: |  | Results (2019) |  | Updated Target Results: | 2021 Results
1. To reduce levels of wasting in children under-five from 7.1% to <5% and wasting in children 6-10 years old from 8.6% to <5% |  | 1. Nutritionally vulnerable population have physical access to safe, clean and potable water supply. |  | Decrease in the number of nutritionally at-risk pregnant women
2. To reduce the proportion of nutritionally at-risk pregnant women from 24.8% to 20.0% |  | 2. Nutritionally vulnerable population have physical access to safety-managed sanitation facilities. |  | Decrease in the prevalence of low birth weight
3. To reduce the prevalence of low birthweight from 21.4% to 16.6% |  | 3. Nutritionally vulnerable population are reached by WASH educational campaign to effect proper hygiene practices. |  | Improved care practices of caregivers among children
Improvement in the number of households meeting energy requirement
Improvement in the availability and access to food of the most vulnerable population
Project/Strategy/Output |  | 2017-2018 accomplishments | 2022 target | 2019-2022 accomplishments | Agency/ies involved
Nutrition in Health
Improving access to Water, Sanitation, and Hygiene (WASH) services
104. | Eligible LGUs endorsed to DBM for release of project’s financial subsidy (SALINTUBIG) |  | 134 (100%) (2020) |  | DILG
105. | Capacity Development Assistance to LGUs on WASH Sector Assessment and Planning |  | 45 (27%) |  | DILG
Improving access to Health and family planning services
106. | Adolescents provided with Adolescent Health and Development (AHD) information |  | 170000 |  | PopCom
107. | Adults (parents, teachers, service providers) provided with AHD information |  | 5100 |  | PopCom
Nutrition in Agriculture
Improving income through agricultural technology
Production Support Sub-Program
108. | LGUs assisted with production support services |  | 82 provinces |  | DA
109. Beneficiaries provided with production support services |  |  |  |  | DA
a. | No. of individual beneficiaries |  | 1407475 |  | DA
b. | No. of group beneficiaries |  | 13, 416 |  | DA
110. No. of inputs provided |  |  |  |  | DA
a. | Seeds provided, kgs |  | 30,882,964.952 |  | DA
b. | Planting materials distributed, kgs |  | 11,580 |  | DA
c. | Animals distributed, head |  | 249,316 |  | DA
d. | Biological control agents distributed, pc |  | 828,350 |  | DA
e. | Biologics, vaccines and drugs distributed, dose |  | 3, 397, 273 |  | DA
f. | Farm supplies distributed, number |  | 390, 821 |  | DA
g. | Farm inputs distributed. Kgs |  | 84, 506 |  | DA
h. | Botanical pesticides distributed, L |  | 700 |  | DA
i. | Fertilizers and other soil ameliorants distributed |  | 225, 131, 576 |  | DA
j. | Semen straws distributed, number |  | 273, 984 |  | DA
k. | Livelihood projects implemented, number |  | 410 |  | DA
l. | Fishering gear/paraphernalia distributed, number |  | 9, 124 |  | DA
m. | Broodstocks distributed, pcs |  | 5,870,000 |  | DA
n. | Seaweed Propagules, kgs |  | 769, 760 |  | DA
o. | Seaweed Farm Implements, set |  | 372 |  | DA
p. | Seaweed nurseries established, number |  | 20 |  | DA
q. | Cages for livelihood, number |  | 3 |  | DA
r. | Mariculture parks maintained, number |  | 37 |  | DA
Research and Development (R&D) Support Services
111. Biofortification and Product Development
a. | Technologies transferred/commercialized |  | 13 |  | DA
b. | Technologies developed |  | 44 |  | DA
c. | R&D activities conducted |  | 2 (2021) |  | DA
Extension Support, Education, and Training Services (ESETS) Sub-Program
112. | Farmers and Fisherfolk Trained |  | 57869 |  | DA (NRP, NCP, HVCDP, NLP, NOAP, HFIDP, SAAD, BFAR)
113. | Trainings conducted (TOT, SOA, FFS, Other trainings) |  | 2959 |  | DA (NRP, NCP, HVCDP, NLP, NOAP, HFIDP, SAAD, BFAR)
114. | Techno demo farm established/maintained |  | 2211 |  | DA (NRP, NCP, HVCDP, NLP, NOAP, HFIDP, SAAD, BFAR)
115. | Learning sites established/maintained |  | 180 |  | DA (NRP, NCP, HVCDP, NLP, NOAP, HFIDP, SAAD, BFAR)
Agricultural Machinery, Equipment, Facilities Sub-Program
116. | LGUs provided to construct agricultural facilities, provinces |  | 83 |  | DA (NRP, NCP, HVCDP, NLP, NOAP
117. | Beneficiaries provided with agricultural machinery, equipment, and facilities, groups |  | 8778 |  | DA (NRP, NCP, HVCDP, NLP, NOAP
Agricultural Insurance
118. | No. of farmers and fisherfolk covered by insurance |  | 2291897 |  | DA-PCIC
Improving physical access to food of nutritionally-vulnerable population
119. | Kadiwa ni Ani at Kita” events conducted |  | 660 |  | DA-NHVCDP
Milk Feeding Program
120. | LGUs with dairy coops linked with gov’t agencies and procuring fresh milk for feeding programs |  | 51 |  | DA-NDA and PCC
C. Food Production in School
121. | Schools provided with production inputs under Gulayan sa Paaralan Program | GPP complements the Dep Ed's School Based Feeding Program (SBFP) by providing basic training on food production (3-day training on vegetable production for GPP focals) DA provided seed and technical support to 5,018 target elementary schools. Each school is allocated a budget of Php12,000. In some instances, a portion of this support is used for an awards mechanism. IIRR and DepEd developed the Integrated School Nutrition Model (ISNM) that, among others, involves the maintenance and school gardens and the use of produce from these gardens for dietary supplementation in the school. - 273 schools trained on the ISNM model - Good practices through mini documentaries and audiovisual presentations have been documented - School Crop museums for conservation and distribution of planting materials have been established in 520 schools - Lighthouse Schools to serve as learning hub on sustainable gardening strategies have been established in 273 schools | 3132 |  | DA-NHVCDP
Nutrition in Social Protection
Improving access to CCT Program
122. | Number of Conditional Cash Transfer (CCT) beneficiaries covered | 4,250,272 or 96.6% Household Profile: 1. Female Grantees: 3,628,866 (85.4%) 2. Children 0-2 yo: 63,952 or 0.7% 3-5 yo: 226,509 or 2.6% Means of Verification: Pantawid Pamilya Information System (PPIS) | 4,400,000 (100%) |  | DSWD
123. | Compliance on health and nutrition conditionality of CCT beneficiaries | 2019: 97.89% P5 2020: 98.01% For Health, 100.0% compliance of the households is attributed to the suspension of all program conditions in support to the Proclamation No. 922, s.2020 declaring a State of Public Health Emergency throughout the Philippines due to the Corona Virus Disease (COVID-19)"; thus, all monitored beneficiaries are deemed compliant in all conditions from March to September 2020 | 100% |  | DSWD
124. | Compliance on FDS conditionality | 100%; For FDS, 100.0% compliance of the households is attributed to the suspension of all program conditions in support to the Proclamation No. 922, s.2020 declaring a State of Public Health Emergency throughout the Philippines due to the Corona Virus Disease (Covid 19)"; thus, all monitored beneficiaries are deemed compliant in all conditions; Use of electronic FDS (eFDS) posted in FB page of Pantawid Pamilyang Pilipino Program | 100% |  | DSWD
125. | Compliant HH for either health or education conditionality provided with rice subsidy |  | 100% |  | DSWD
Improve access to Sustainable Livelihood Program of the nutritionally vulnerable households/population
126. | No. of households in PPAN priority areas provided with SLP modalities for Microenterprise Development | As of December 2020, HOUSEHOLD LEVEL: - SLP served 20,338 households in PPAN priority areas provided through Program Modalities - 93.38% or 18,991 households have already engaged in microenterprise in PPAN priority areas | 20,338 (2020) |  | DSWD
127. | No. of households in PPAN priority areas provided with SLP modalities for Employment Facilitation | 0.27% or 54 households were successfully employed or engaged in Employment Facilitation in PPAN priority areas. | 54 (2019) |  | DSWD
Nutrition in Education
128. | Provision of Financial Assistance to Lighthouse Schools to Sustain the Advocacy on ISNM Integrated School Nutrition Model | 213 Schools (1 school per SDO) (100%); Lighthouse schools will feature a regular school feeding program, maintained/sustained bio intensive garden and school-based nutrition education activities | 223 Schools (1 school per SDO) |  | DepEd
129. | Expansion of Gulayan sa Paaralan (GPP) implementation to all public schools nationwide through provision of program support funds to selected schools with minimal implementation or no established GPP. (DepEd) | 41,000 schools with established GPP (SY 2019-2020); Provision of program support funds to selected schools for the establishment of GPP | 5,000 additional schools (from 5th & 6th class municipality) |  | DepEd | `
130. | Adolescent Reproductive Health (ARH): Weekly Iron Folic Acid Supplementation for Female Adolescent Learners in Public High School | 8,804,976 Female adolescent learners (70% of enrolled female learners); WIFA Supplementation is a collaborative activity between DOH and DepEd for Grades 7-12 and ALS female learners Implementation: July to September=1 tablet per week January to March = 1 tablet per week | 9245224 |  | DepEd
131. | Deworming of the enrolled learners | 85% of the enrolled learners; All school-aged children ages 5 to 17 years old in public elementary schools will be dewormed for one (1) month through the National Schools Deworming day initiatives. The deworming activity will be conducted twice a year in July (round 1) and January (round 2). For Soil-Transmitted Helminthiasis, an Administrative Order No. 2010-0023 issued by the DOH recommends Albendazole 400mg 1 tablet per learner. | 100% |  | DepEd
5. WASH in Schools (WinS) (DepEd)
a. | Public schools with water for cleaning and daily handwashing available at all times. | 21,033 schools or 44.7% of public schools with water for cleaning and daily handwashing available at all times. | 30000 |  | DepEd
b. | Learners provided with supply of soap for handwashing and toothbrush with toothpaste for brushing of teeth. | 13,000,000 learners provided with supply of soap for handwashing and toothbrush with toothpaste for brushing of teeth. | 13,000,000 kinder to grade 6 learners |  | DepEd
133. | Accredited Centers using the Standards and Guidelines for Center-based Early Childhood Programs for 0 to 4 Years Old Filipino Children (DSWD) | based on 4,864 accreditation of service providers, General Appropriations Act (GAA) for 2020-2022 | 4864 |  | DSWD
134. | Enrolled learners attending adolescent Reproductive Health (ARH): Comprehensive Sexuality Education | 100% of enrolled learners; CSE enhances the over-all wellness of the Filipino adolescents (physical, mental, emotional, social and spiritual) by enabling teachers to integrate key concepts and messages on reproductive health concerns across the curriculum wherever these can be done most appropriately. | 100% |  | DepEd
135. | National Child Development Center (NCDCs) with Infant-Toddler Early Development (ITED) Program | Based on existing 772 National Child Development Center (NCDCs), as of 2020 | 100 |  | ECDC
136. | National Child Development Center (NCDCs) with Family Support Program | Based on existing 772 National Child Development Center (NCDCs), as of 2020 | 100 |  | ECDC
137. | Parentings Effectiveness Sessions conducted |  | 1,505,583 (80%) |  | DSWD
Nutrition in Trade and Industry
Increasing access to food
138. | LGUs in the PPAN priority provinces assisted in the establishment of food plants for the production of complementary foods and other food supplements |  | 4 |  | DTI
3. | LGUs assisted in the establishment of food plants for the production of complementary foods and other food supplements |  | 4 |  | DTI

## LGU Mob
Mobilization of LGUs for Nutrition Outcomes. Recognizes the key role of LGUs in achieving targeted nutritional outcomes. It aims to ensure sustained advocacy and capacity building of local government units particularly local chief executives and local nutrition teams on integrating nutrition in local development plans and budgets and on effective nutrition program management, nutrition leadership and governance.
Target Results: |  | Results (2019) |  | 2021 Results
At least 70% of PPAN/HDPRC focus provinces, cities and municipalities deliver positive nutritional outcomes (stunting) which is equivalent to 22 out of the 32 focus provinces, 48 out of 69 cities (HUCs and CC), and 499 out of 714 municipalities
Project/Strategy/Output |  | 2017-2018 accomplishments | 2022 target | 2019-2022 accomplishments | Agency/ies involved
Formulation of Local Nutrition Action Plans for 2020-2022 and Integration into local development plans and budgets
140. | Provinces, Cities and Municipalities in the PPAN-HDPRC with approved LNAP | LNAP Workshops conducted in the 32 HDPRC focus provinces. | 7 |  | NNC, LGUs
141. | Provinces, cities and municipalities in PPAN HDPRC areas integrated nutrition in PDPFP, CDP, LDIP | This was first done in 2018, with the objective of integrating nutrition in the 2019 AIP. Conducted in 22 provinces, 48 cities and 499 municipalities | 7 |  | NNC, LGUs
142. | Provinces, cities and municipalities in PPAN HDPRC areas integrated nutrition in Annual Investment Programs (AIP) | The series of workshops were conducted in the same number of LGUs and was piloted in the LGUs of ARMM in 2018 | 7 |  | NNC, LGUs
143. | Nutrition Program costing tools for LNAP formulation developed and disseminated | Developed based on the exercise done in 2018, and served as template for the planning workshops for 2020-2022 LNAP and the basis for the integration in AIP for 2021-2022 | 1 (for AIP 2021) |  | NNC, LGUs
Advocacy interface with Local Chief Executives (LCEs) on Investing in Nutrition
144. | Nutrition Champions Program established and implemented | The program started early this year but was suspended due to COVID 19. Formal establishment will happen in 2021. | 1 (2021) |  | NNC
145. | Enlisted LCEs as nutrition champions mobilized for advocacy activities | Eight LCEs enlisted as nutrition champions but the program was suspended due to COVID19. | 10 (2021) |  | NNC
146. | Advocacy tools (Compendium of Actions on Nutrition, Compendium of Local Ordinances on Nutrition, P/C/M/B NPM Brochure) developed and disseminated | The Compendium of Actions for Nutrition (CAN) was printed and disseminated to concerned partners and stakeholders. It is being use continuously for advocacy activities. The Compendium of Local Ordinances on Nutrition was launched on 01 October with an Online Portal. Printing and dissemination will happen in 2021. Ongoing reproduction of 45,000 copies of Barangay NPM Brochure to be distributed in all barangays in the Philppines | 1 (2021) |  | NNC
147. | Strong linkages between regional mobilization groups, RICs and local BNC, BNS, and MNC/CNC established. |  | / |  | NNC, CSOs

## Policy
Policy development for food and nutrition. The ultimate goal in the current period of the PPAN 2017-2022 is to secure important policies in the form of legislation and administrative issuances, and budgetary support that will enable the NGAs and the LGUs to implement the PPAN more robustly.
Target Results: |  | Results (2019) |  | 2021 Results
90% of the planned policy agenda achieved
85%of estimated budgetary requirements for PPAN implementation allocated and 95% of allocation disbursed (Target removed in updated RF)
Project/Strategy/Output |  | 2017-2018 accomplishments | 2022 target | 2019-2022 accomplishments | Agency/ies involved
148. Legislative proposals passed
a. | Amendment of PD 1569 on the Barangay Nutrition Scholar Program (NNC) |  | 1 (2021) |  | NNC
b. | Program Strengthening and Institutionalization of the First 1000 Days Program, including concerns on maternity protection (DOH, NNC) | RA 11148 or the Kalusugan at Nutrisyon ng Mag-Nanay Act on the first 1000 days was enacted into law in 2018. | 1 (2018) |  | NNC, DOH
c. | Maternity protection, i.e. extended maternity leave (DOH, DOLE) | RA 11210 or the 105- Expanded Maternity Leave Law was enacted into law on 20 February 2019. | 1 (2019) |  | DOH, DOLE
d. | Mandatory plantilla positions for nutrition action officers (NNC) |  | 1
e. | Taxation on Sugar-Sweetened Beverages | Integrated in the TRAIN Law or RA 10963 passed on 2019 | 1 (2017) |  | DOH, NNC
149. Administrative issuances adopted
a. | ASEAN Leaders’ Declaration on Ending All Forms of Malnutrition (ASEAN Secretariat, NNC) | Adopted in November 2017. Strategic Plan to operationalize the ALD formulated in May 2018 | 1 (2017) |  | ASEAN Secretariat, NNC
b. | Executive Order on PPAN implementation (Office of the President, NNC) | NNC submitted draft to the Office of the President but the effort has not progressed. | 1 (2021) |  | Office of the President, NNC
c. | DILG issuance on PPAN implementation (DILG, NNC) | DILG MC 2018-42 issued in enjoins LGUs to prioritize allocation of local fund of PPAs included in the LPANs that are in turn based on the PPAN. This was followed by the Joint Memorandum Circular for DOH, DILG and NNC (JMC 2019-001), signed on November 2019, with the same intent on enjoining LGUs to identify and prioritize PPAs for nutrition or 2020-2022 based on the PPAN 2017-2022. | 1 (2018) |  | DILG, NNC
d. | Inclusion of nutrition programs in national and local budget issuances (DBM, NEDA, NNC) | DBM issued Local Budget Memorandum 77, 77-a (For Barangays, 78, and 80 in 2018 and 2019 and 2020, respectively. Both memoranda included nutrition programs among priority programs for inclusion in the local budget for 2019 and for 2020. National Budget Memorandum No. 130 of 2018 included nutrition programs among priorities for Tier 2 budget proposals for 2019. National Budget Memorandum No. 131 of 2019 identified RA 11148 as among legislations that would require funding under the budget for 2020. | 1 (2020) |  | DBM, NEDA, NNC
e. | Nutrition program for government workers (NNC) |  | 1 (2019) |  | NNC
f. | Guidelines on Non- Wood Height- Measuring Tools (NNC) | NNC GB Resolution No. 3 Series 2018 (April 2018) | 1 (2018) |  | NNC
g. | Guidelines on the Integration of Gender Concerns in Nutrition Policies Plans and Programs (NNC) | Still to be done for 2020 | 1 (2021) |  | NNC
h. | On funding sources for LGU nutrition programs (DILG, DBM, NNC) | Instead of an issuance only on funding source for nutrition programs, DOH-DILG Joint Memorandum Circular (JMC) No. 1 of 2019 identified nutrition programs and projects that can be integrated in local development plans and annual investment programs. A section of the JMC is on financing that indicates the local budget may fund local nutrition programs and projects. |  |  | DILG, DBM, NNC
i. | Guidelines for Assessing the Nutritional Status of Pregnant Women | The concern will be integrated in the DOH policy on maternal nutrition that is being developed
j. | RNC policies |  | 16 |  | NNC
k. | Regulation of the Marketing of Foods of Poor Nutritional Quality for Children |  | 1 (2021) |  | NNC, DOH
150. Policies reviewed
a. | RNC policies |  | 16 |  | NNC
Public Advocacy for Improved Support to Nutrition in the Philippines
151. | Policy Forum |  | 1 |  | NNC

## MGT Support
Strengthened management support to PPAN. This program aims to improve the efficiency and effectiveness of improving the efficiency and effectiveness in the planning, implementation, and overall management of the nutrition specific and nutrition sensitive programs.
Project/Strategy/Output |  | 2017-2019 accomplishments | 2022 target | 2019-2022 accomplishments | Agency/ies involved
Formulation of Local Nutrition Action Plans for 2020-2022 and Integration into local development plans and budgets
152. | Resource (human, financial, and organizational) generation and mobilization strategy formulated and implemented | Still to be done | 1 (2020) |  | NNC
153. | Structures for coordination (NNC Governing Board, NNC Technical Committee, Program Technical Working Groups, Regional Nutrition Committees, Regional Technical Working Group, Scaling Up Nutrition Movement Networks and others (as may be organized) are functional. | All multi-stakeholder coordinating structures are in place and supported by policies to ensure sustainability (source: SUNJA Report). However, sectoral focal points from the NNC Secretariat are yet to be designated (source: PPAN Review). | / |  | NNC
154. PPAN 2017-2022 and related plans formulated and updated
a. | PPAN Results Framework |  | 16 (2021) |  | NNC, NGAs, LGUs
b. | Regional Plan of Action for Nutrition (RPAN) | 17 (100%) | 17 (2017) |  | NNC, NGAs, LGUs
c. | Provincial, City, Municipal Nutrition Action Plans | 88.9% for 2018 | 89% (2018) |  | NNC, NGAs, LGUs
155. | Guidelines for PPAN monitoring and evaluation adopted and implemented | The NNC Governing Board has approved the Local Government Nutrition Monitoring and Evaluation System (LGNMES) or the MELLPI Pro as part of PPAN M&E system. Training and roll-out was conducted in 2018 and implemented by NNC Regional Offices and LGUs in 2019. | / |  | NNC
156. | Philippine Food and Nutrition Surveillance System updated and functional | A consulting firm was engaged to assist in formulating the Philippine Nutrition Surveillance System Strategic Plan. The plan has been drafted and will be finalized in 2020 for implementation up to 2022. | / |  | NNC
157. | Annual reports on physical and financial accomplishments prepared |  | 1 |  | NNC
158. | Program implementation review undertaken at national and regional levels |  | 18 |  | NNC
159. | PPAN research agenda formulated and implemented |  | / |  | NNC